## Slide 1
VA · AGENTIC MIGRATION
01 / 11
30 · 60 · 90 DAY PLAN
From deterministic dialog flow to a supervised agentic system.
A focused 90-day migration: stand up the supervisor, ship a 3-domain MVP, then take all 7 domains into a pilot behind the apperian flag.
PROGRAM WINDOW
May 22 — Aug 19, 2026
AUDIENCE
Engineering · Architecture review
ROLLOUT
apperian flag · Pilot ~100 users

## Slide 2
CONTEXT
02 / 11
The shift in a single picture.
Hard-coded routing & static intents give way to a supervisor agent, probabilistic intent, and per-domain sub-agents calling Tools.
TODAY · DETERMINISTIC
Dialog-flow VA
Rule-based intent matching & rigid follow-ups
Monolithic dialog flows per experience
FAPI endpoints called directly from flows
Hard-coded UI & copy per turn
Single deploy path; no parallel routing
TARGET · AGENTIC
Supervisor + 7 domain sub-agents
Probabilistic intent (ML + LLM) with follow-ups
Domain sub-agents: Transactions, Cards, Insights, Rates / Fees / Limits, Answer Hub, Advice, Money Movement
FAPI endpoints wrapped as Tools
Widget builders per experience
chat-api & orchestrator route via apperian flag

## Slide 3
WORKSTREAMS
03 / 11
Seven parallel tracks land the migration.
Sub-agents & prompts are days of work; Tools and Widget builders are the heavy lift — Devin playbooks accelerate both.
01
Supervisor agent
New instance. Intent routing to sub-agents; conversation & tool-call orchestration.
CORE
02
Intent & follow-up classifier
Probabilistic. ML + LLM combined for intent resolution and follow-up disambiguation.
CORE
03
Domain sub-agents & prompts
Seven domains. Per-agent prompts & tool bindings. ~5 days of focused build.
~5 DAYS
04
Tools (FAPI → Tools)
Convert existing FAPI endpoints into typed Tools consumable by sub-agents.
HEAVY · DEVIN
05
Widget builders
One per experience. Renders the structured response from each sub-agent.
HEAVY · DEVIN
06
chat-api & orchestrator
Apperian-flag-aware routing to the parallel agentic stack; response shape parity.
INTEGRATION
07
Test harness & rollout
Fargo agent builder + test harness automate most coverage. Pilot via apperian flag.
CONTINUOUS
Accelerators
Devin playbooks for Tool / Widget scaffolds. Fargo for harnessing. ACE, Tachyon, ECM partner support.
CROSS-CUTTING

## Slide 4
THE 30 · 60 · 90
04 / 11
The 90-day path, by workstream.
PHASE 1 · DAYS 1–30
Enablement
May 22 → Jun 20, 2026
PHASE 2 · DAYS 31–60
MVP · 3 domains
Jun 21 → Jul 20, 2026
PHASE 3 · DAYS 61–90
Full coverage & pilot
Jul 21 → Aug 19, 2026
D0 · May 22
D30 · Jun 20
D60 · Jul 20
D90 · Aug 19
Supervisor agent
BUILD
Intent & follow-up (ML + LLM)
TRAIN v0
TUNE
EXPAND
Sub-agents & prompts (7)
MVP · 3
+ 4
Tools · FAPI → Tools (Devin)
FRAMEWORK
MVP TOOLS
REMAINING TOOLS
Widget builders (Devin)
FRAMEWORK
MVP WIDGETS
REMAINING
chat-api & orchestrator (apperian)
FLAG WIRING
ROUTE PARITY
Test harness (Fargo) & rollout
INTEGRATE
MVP COVERAGE
FULL COVERAGE
PILOT

## Slide 5
PHASE 1 · ENABLEMENT
05 / 11
Stand up the agentic plumbing.
D1 – D30 · May 22 → Jun 20, 2026
Goal: every foundational piece is in place so MVP build in Phase 2 can move at full speed. No new domain experiences ship yet.
BUILDS
Supervisor agent v0 — new instance, intent → sub-agent routing
CORE
Intent & follow-up classifier v0 (ML + LLM)
PROBABILISTIC
Tools framework + Devin playbook for FAPI → Tool conversion
SCAFFOLD
Widget builder framework + Devin playbook
SCAFFOLD
chat-api & orchestrator: apperian-flag routing design + dev
INTEGRATION
Fargo agent builder + test harness wired into CI
QUALITY
PARTNER ENABLEMENT (IN-FLIGHT)
ACE — repos & CI/CD pipeline stood up
2–3 WEEKS DEDICATED
Tachyon — keys + Arise spaces for each agent
7 AGENTS · ALL ENVS
ECM — data ingestion pipelines kicked off
SOURCE FEEDS
Prod Ops — expedited deploy path aligned (hard-gate only)
PRE-NEGOTIATED
EXIT CRITERIA
Repos green, agent skeletons deployable to lower envs
GATE TO PHASE 2

## Slide 6
PHASE 2 · MVP
06 / 11
Three domains, end to end.
D31 – D60 · Jun 21 → Jul 20, 2026
Prove the architecture with Advice, Answer Hub, and Transactions — the lowest-risk, highest-traffic mix. Internal-only behind the apperian flag.
DOMAINS LIVE (LOWER ENVS)
Advice
SUB-AGENT · TOOLS · WIDGETS
Answer Hub
SUB-AGENT · TOOLS · WIDGETS
Transactions
SUB-AGENT · TOOLS · WIDGETS
VALIDATION
End-to-end coverage via Fargo test harness
REGRESSION + EVAL SETS
Intent classifier tuned on MVP-domain traffic
PRECISION ≥ DIALOG PARITY
INTEGRATION
chat-api / orchestrator route via apperian flag — parity-checked
SHAPE + LATENCY
Tools framework hardened, MVP Tools production-shaped
TYPED CONTRACTS
Widget builders meet design parity for MVP turns
UX REVIEW
EXIT CRITERIA
3-domain MVP soak-tested in pre-prod
GATE TO PHASE 3
Hard-gate requirements drafted for expedited prod path

## Slide 7
PHASE 3 · FULL COVERAGE
07 / 11
Remaining four domains, then pilot.
D61 – D90 · Jul 21 → Aug 19, 2026
Bring the rest of the surface online and take all seven domains into a pilot — ~100 users behind the apperian flag, parity-tested against the top-50 intents.
REMAINING DOMAINS
Cards
SUB-AGENT · TOOLS · WIDGETS
Insights
SUB-AGENT · TOOLS · WIDGETS
Rates / Fees / Limits
SUB-AGENT · TOOLS · WIDGETS
Money Movement
SUB-AGENT · TOOLS · WIDGETS · HIGH-RISK
LAUNCH
Expedited prod deploys via hard-gate path, no dark-mode release
PROD OPS
Pilot live on apperian flag — ~100 users
NORTH STAR
Top-50 intent parity validated against deterministic baseline
EVAL HARNESS
Monitoring, drift detection, & rollback plan in place
OPERATIONAL

## Slide 8
ASKS
08 / 11
Partner team support — what we need, when.
Four partner teams sit on the critical path. The earliest two (ACE, Tachyon) must be confirmed before Day 1.
TEAM
ASK
WINDOW
IF DELAYED
ACE
Dedicated support to enable repos and the CI/CD pipeline for supervisor + 7 sub-agents.
D1 – D21 · 2–3 weeks
Blocks every build track. Phase 1 slips immediately.
Tachyon
Keys provisioned for each agent and Arise spaces across all environments.
D1 – D28
Sub-agents cannot be exercised end-to-end without keys.
ECM
Data ingestion support for sub-agent grounding sources and evaluation sets.
D5 – D45
Answer Hub and Advice quality regress without grounding.
Prod Ops
Expedited prod deploys after hard-gate sign-off — without the standard dark-mode release.
D75 – D90
Pilot push slips past the Aug 19 north star.

## Slide 9
RESOURCING
09 / 11
Where the team is pointed.
Six workstreams running in parallel. Devin and Fargo absorb the most repetitive scaffolding so human effort goes to integration and quality.
CORE AGENTS
Supervisor & Intent
Builds supervisor instance, intent & follow-up classifier, sub-agent prompts.
2 ENG · ML PARTNER (PART-TIME)
HEAVY LIFT
Tools & Widgets
FAPI → Tool conversions and per-experience widget builders. Devin playbooks accelerate.
4 ENG · DEVIN PLAYBOOKS
INTEGRATION
chat-api & orchestrator
Apperian-flag routing, response-shape parity, latency & observability work.
2 ENG
QUALITY
Test harness & eval
Fargo agent-builder harness, eval sets, regression coverage, drift checks.
1 ENG · QA PARTNER
PROGRAM
PM & partner ops
Drives ACE / Tachyon / ECM / Prod Ops. Owns the apperian flag plan and pilot.
1 PM · 1 TPM
CROSS-CUTTING
Architecture & review
Reviews, design alignment, security & risk sign-off across all workstreams.
1 ARCHITECT · PART-TIME

## Slide 10
RISKS & DEPENDENCIES
10 / 11
What could move the Day-90 date.
R-01
ACE bandwidth slip
Repos / CI-CD enablement takes longer than the requested 2–3 weeks.
MITIG · LOCK ACE BEFORE D1
R-02
Tools effort underestimated
FAPI surface is larger / less typed than expected; per-Tool conversion cost rises.
MITIG · DEVIN PLAYBOOK + SCOPE FREEZE
R-03
Intent classifier quality
Probabilistic ML+LLM misroutes top-50 intents under live traffic patterns.
MITIG · EVAL HARNESS + GUARDRAILS
R-04
Widget builder fan-out
Per-experience widgets multiply quickly across the 7 domains.
MITIG · SHARED BUILDER FRAMEWORK
R-05
Expedited deploy denied
Standard dark-mode release imposed despite hard-gate readiness.
MITIG · PROD OPS ALIGNMENT BY D60
R-06
Money Movement complexity
Highest-risk domain compresses into the last two weeks of Phase 3.
MITIG · KICK OFF DESIGN IN PHASE 2

## Slide 11
DAY 90 · NORTH STAR
11 / 11
All seven domains live behind the apperian flag. Pilot ~100 users. Parity on top-50 intents.
LANDING DATE
Aug 19, 2026
COVERAGE
7 sub-agents · supervisor · probabilistic intent
VALIDATED AGAINST
Top-50 intents · deterministic baseline